## Overview
SUNOTAL QUICK COMMERCE — COMPREHENSIVE ENHANCEMENT REPORT
Generated: 30 September 2026 ¦ Total Enhancements: 297 ¦ Applications: User · Admin · Vendor · Delivery · Support · Monitoring
# | Category / Sheet | # Items | Critical | High | Medium | Low | Timeline | Your Progress
1 | Application Features | 84 | 0 | 60 | 24 | 0 | Weeks 1-8 | ⬜ Not Started
2 | UI-UX Enhancements | 44 | 0 | 28 | 16 | 0 | Weeks 1-8 | ⬜ Not Started
3 | DB Query CRUD Optimization | 34 | 0 | 22 | 12 | 0 | Weeks 1-8 | ⬜ Not Started
4 | Dockerfile Optimization | 18 | 0 | 12 | 5 | 1 | Weeks 1-8 | ⬜ Not Started
5 | DockerCompose Optimization | 17 | 0 | 10 | 6 | 1 | Weeks 1-8 | ⬜ Not Started
6 | Terraform Code Optimization | 20 | 0 | 13 | 6 | 1 | Weeks 1-8 | ⬜ Not Started
7 | Workflow Optimization | 25 | 0 | 19 | 6 | 0 | Weeks 1-8 | ⬜ Not Started
8 | System Design Optimization | 21 | 0 | 15 | 6 | 0 | Weeks 1-8 | ⬜ Not Started
9 | Business Logic Corrections | 34 | 7 | 21 | 6 | 0 | Weeks 1-8 | ⬜ Not Started
TOTAL ENHANCEMENTS |  | 297

## QC Features Reference
WORLD-CLASS QUICK COMMERCE FEATURES — GLOBAL + INDIA BENCHMARK
🏭 | DARK STORE NETWORK | Hyperlocal 2-3km radius micro-warehouses with 2,000-5,000 SKUs for 10-min delivery
🤖 | AI DEMAND FORECASTING | ML models predict demand per zone/hour — reduces waste 30%, OOS 40% (Zepto, Blinkit)
🗺️ | SMART ORDER DISPATCH | Geospatial nearest-rider auto-assignment within 30 seconds of order placement
📡 | REAL-TIME GPS TRACKING | WebSocket-based live rider tracking with traffic-aware ETA recalculation
🔄 | SUBSCRIPTION DELIVERY | Daily milk/eggs recurring orders with UPI Autopay — BigBasket BB Daily model
💰 | DYNAMIC SURGE PRICING | Time/demand-based delivery fee adjustment — Uber model applied to quick commerce
🎮 | GAMIFIED RIDER INCENTIVES | Daily/weekly streak bonuses, badges, leaderboards — reduces rider churn 40%
🌐 | ONDC INTEGRATION | India Open Network for Digital Commerce — expand to 250M+ ONDC network buyers
📱 | VOICE COMMERCE | Multilingual voice search (Telugu, Hindi, English) — 60% Tier-2 users prefer voice
💳 | UPI AUTOPAY MANDATES | Recurring mandate for subscriptions — India preferred payment rail (1.4B users)
🎁 | LOYALTY PROGRAM | Zepto Pass / Blinkit Club — subscription with free delivery + exclusive deals
📦 | BATCH DELIVERY | Club 2-3 orders per rider trip — reduces cost per delivery by 35%
❄️ | COLD CHAIN MANAGEMENT | Temperature monitoring from dark store to doorstep for dairy/meat/ice cream
⚡ | 10-MIN SLA PROMISE | Prominent UI countdown + penalty refund if missed — primary brand differentiator
🌿 | FRESHNESS GUARANTEE | Return/replace without questions for fresh produce — Zepto/Blinkit standard
📊 | UNIT ECONOMICS TRACKING | Cost per delivery, GMV/rider, waste %, OOS rate — operational KPI dashboard
🔗 | eNAM + ONDC | Direct mandi price integration — enables fair direct procurement from farmers
🛡️ | FSSAI COMPLIANCE | Food safety license validation for all food vendors — regulatory requirement
📲 | WHATSAPP COMMERCE | Order via WhatsApp chatbot — 530M WhatsApp users in India for Tier-2/3 markets
🌱 | CARBON TRACKING | CO2 per delivery metric — ESG reporting for corporate/enterprise customers

## Application Features
APPLICATION FEATURES — SUNOTAL ENHANCEMENTS (84 items)
Mark Done? column with ✓ when completed ¦ Priority: CRITICAL > HIGH > MEDIUM > LOW
Done? | # | Service / Module | Enhancement / Recommendation | Priority | Business Rationale | Current Status | Timeline | Notes / Remarks
☐ | 1 | User App | Social Login (Google / Facebook / Apple Sign-In) | HIGH | Reduces friction, increases conversion rate by 30-40% | Missing | Week 1-2
☐ | 2 | User App | One-Tap Reorder from previous orders | HIGH | Zepto/Blinkit core feature — drives repeat orders | Missing | Week 2
☐ | 3 | User App | Voice Search (multilingual: English + Telugu + Hindi) | HIGH | India-specific: 60% rural users prefer voice search | Missing | Week 2-3
☐ | 4 | User App | Smart AI Personalized Recommendations (ML-based) | HIGH | Increases AOV by 25%, used by Instamart/Blinkit | Missing | Week 3-4
☐ | 5 | User App | Real-time Stock Availability indicator per product | HIGH | Critical for quick commerce — avoid order failures | Partial | Week 1
☐ | 6 | User App | Subscription / Daily Recurring Orders (milk, eggs, bread) | HIGH | BB Daily model — Rs500Cr+ opportunity in India | Partial (DB schema only) | Week 2-3
☐ | 7 | User App | In-App Live Chat with rider (WhatsApp-style) | HIGH | Reduces support tickets 40%, Zepto feature | Missing | Week 3
☐ | 8 | User App | 10-minute delivery promise with dynamic ETA | HIGH | Core quick commerce SLA — must show on UI prominently | Partial (backend only) | Week 1
☐ | 9 | User App | Dynamic Substitution suggestions when item OOS | HIGH | Reduces cart abandonment by 30% | Missing | Week 2
☐ | 10 | User App | Group Order / Split Cart feature | MEDIUM | Trending — Gen Z feature, used by Swiggy Instamart | Missing | Week 4
☐ | 11 | User App | Product Bundle Deals (Buy 2 get 1, combo packs) | MEDIUM | Increases AOV — used by BigBasket, Zepto | Missing | Week 3
☐ | 12 | User App | Loyalty Points / Reward System (Sunotal Coins) | MEDIUM | Increases retention — standard in all q-commerce | Missing | Week 4-5
☐ | 13 | User App | Refer & Earn with tracking dashboard | MEDIUM | Viral growth loop — standard in Indian q-commerce | Missing | Week 3
☐ | 14 | User App | ONDC Protocol Integration | HIGH | India mandated — expand to ONDC network buyers | Missing | Week 6-8
☐ | 15 | User App | Multiple Payment: UPI, BNPL (Simpl/LazyPay), COD | HIGH | COD accounts for 60% orders in Tier-2/3 India | Partial | Week 1-2
☐ | 16 | User App | UPI Autopay for subscriptions | MEDIUM | Critical for subscription model | Missing | Week 3
☐ | 17 | User App | Scheduled Delivery Slots (morning/evening/custom) | HIGH | India standard: Dmart Ready, Bigbasket BB Now feature | Missing | Week 2
☐ | 18 | User App | Product Rating & Review with photo upload | HIGH | Trust builder — increases conversion by 18% | Partial (rating only) | Week 2
☐ | 19 | User App | Push Notification for price drop, restock, offers | HIGH | Re-engagement driver — Zepto primary retention tool | Missing | Week 2
☐ | 20 | User App | Order cancellation with instant refund to wallet | HIGH | User trust — within 1 min of placing order | Partial | Week 1
☐ | 21 | User App | Age-gated product access (alcohol, tobacco) | HIGH | Legal compliance — needed for category expansion | Missing | Week 4
☐ | 22 | User App | Dark Mode UI | MEDIUM | UX standard — 65% users prefer dark mode | Missing | Week 2
☐ | 23 | User App | Freshness Guarantee badge + easy return policy | HIGH | Trust signal — Dunzo / Bigbasket standard | Missing | Week 2
☐ | 24 | User App | Hyperlocal geo-fenced offers per neighbourhood | MEDIUM | Used by Swiggy for micro-locality promotions | Missing | Week 5
☐ | 25 | User App | Smart Cart (auto-detect missing items from past habits) | MEDIUM | AI-driven convenience — Instamart 2024 feature | Missing | Week 5
☐ | 26 | Delivery App | Turn-by-turn Navigation (Google Maps / Mappls) | HIGH | Critical for 10-min delivery SLA | Missing | Week 1
☐ | 27 | Delivery App | Heat Map of high-demand zones for rider positioning | HIGH | Zepto Surge — positions riders near demand clusters | Missing | Week 3
☐ | 28 | Delivery App | Gamified Incentives (daily targets, badges, streak bonuses) | HIGH | Increases rider retention 40% — Swiggy model | Missing | Week 3
☐ | 29 | Delivery App | Batch Order delivery (2-3 orders in one trip) | HIGH | Reduces delivery cost 35% — Blinkit key innovation | Missing | Week 4
☐ | 30 | Delivery App | Rider SOS / Emergency button | HIGH | Rider safety — legal requirement in some states | Missing | Week 2
☐ | 31 | Delivery App | Contactless delivery mode with photo proof | HIGH | Post-COVID standard — reduces disputes 70% | Missing | Week 2
☐ | 32 | Delivery App | Auto-assign order to nearest available rider | HIGH | Core quick-commerce dispatch engine — MISSING! | Missing | Week 3-4
☐ | 33 | Delivery App | Background location tracking with battery optimization | HIGH | Critical for GPS tracking accuracy | Missing | Week 1
☐ | 34 | Delivery App | Rider insurance claim workflow | HIGH | Legal compliance & welfare — DPIIT guidelines | Missing | Week 4
☐ | 35 | Delivery App | Offline mode for poor connectivity areas | MEDIUM | Tier-2/3 India requirement | Missing | Week 4
☐ | 36 | Delivery App | In-app QR/Barcode scanner for package verification | MEDIUM | Reduces wrong delivery errors | Missing | Week 3
☐ | 37 | Delivery App | Shift management with automatic status update | MEDIUM | Operational efficiency | Missing | Week 3
☐ | 38 | Vendor App | Live Inventory Dashboard with low-stock alerts | HIGH | Real-time visibility reduces OOS incidents | Missing | Week 2
☐ | 39 | Vendor App | Bulk Product Upload via CSV/Excel | HIGH | Operational efficiency for large vendors | Missing | Week 2
☐ | 40 | Vendor App | Vendor-specific analytics: sales, returns, ratings | HIGH | Seller empowerment — Amazon/Flipkart model | Missing | Week 3
☐ | 41 | Vendor App | Direct payment settlement dashboard (UPI/Bank) | HIGH | Financial transparency builds vendor trust | Partial | Week 2
☐ | 42 | Vendor App | Procurement order management (accept/reject bulk orders) | HIGH | Supply chain management core feature | Missing | Week 2
☐ | 43 | Vendor App | eNAM integration (National Agriculture Market) | HIGH | India-specific: connects to government mandi prices | Missing | Week 6-8
☐ | 44 | Vendor App | Auto-generate invoice PDF on sale completion | HIGH | GST compliance requirement | Partial (flag in DB) | Week 2
☐ | 45 | Vendor App | Real-time crop price feed integration (APMC/MSP data) | HIGH | Data-driven procurement — enables fair pricing | Missing | Week 5
☐ | 46 | Vendor App | FPO (Farmer Producer Org) group onboarding | MEDIUM | India-specific — aggregated sourcing from rural cooperatives | Missing | Week 6
☐ | 47 | Vendor App | Harvest schedule calendar for advance procurement | MEDIUM | Reduces stockouts from seasonal supply gaps | Missing | Week 4
☐ | 48 | Vendor App | Barcode / QR code generation per product | MEDIUM | Enables dark store scanning at inbound | Missing | Week 4
☐ | 49 | Vendor App | Price negotiation workflow (counter-offer quotations) | MEDIUM | Dynamic procurement pricing | Missing | Week 4
☐ | 50 | Vendor App | Vendor loyalty tier system (Bronze/Silver/Gold) | MEDIUM | Incentivizes exclusive sourcing partnerships | Missing | Week 5
☐ | 51 | Admin App | Real-time Operations Command Center (live order map) | HIGH | Single pane of glass for ops team — Blinkit Ops feature | Missing | Week 2
☐ | 52 | Admin App | Dynamic pricing engine (AI-based demand/supply pricing) | HIGH | Revenue optimization — Zepto key differentiator | Missing | Week 5-6
☐ | 53 | Admin App | Dark Store inventory heatmap | HIGH | Visual OOS detection across all dark stores | Missing | Week 3
☐ | 54 | Admin App | Fraud detection system (abnormal order patterns) | HIGH | Reduces losses from fake orders, promo abuse | Missing | Week 4
☐ | 55 | Admin App | Customer segmentation & cohort analysis (RFM model) | HIGH | Data-driven marketing — Instamart uses RFM model | Missing | Week 5
☐ | 56 | Admin App | Automated reordering triggers (when stock < threshold) | HIGH | Prevents OOS — critical for 10-min delivery promise | Missing | Week 3
☐ | 57 | Admin App | Multi-city / Multi-dark-store management | HIGH | Scalability requirement for national expansion | Missing | Week 4
☐ | 58 | Admin App | SLA Breach alerting (if order > 15 min, auto-alert ops) | HIGH | Quality control automation | Missing | Week 3
☐ | 59 | Admin App | Revenue forecast & GMV projections dashboard | HIGH | Business intelligence for leadership | Missing | Week 4
☐ | 60 | Admin App | Bulk notification broadcast (WhatsApp/SMS/Push) | HIGH | Campaign management tool | Missing | Week 3
☐ | 61 | Admin App | GSTIN verification & automated GST filing assist | HIGH | Tax compliance — critical for Indian operations | Missing | Week 5
☐ | 62 | Admin App | Coupon & flash sale management with scheduling | HIGH | Marketing ops — standard in all q-commerce | Partial (coupons table) | Week 2
☐ | 63 | Admin App | A/B Testing framework for promotions & UI | MEDIUM | Data-driven decision making | Missing | Week 6
☐ | 64 | Admin App | Vendor scorecard & performance ranking | MEDIUM | Supply chain quality management | Missing | Week 4
☐ | 65 | Admin App | Automated cancellation reason analysis & reporting | MEDIUM | Identifies operational weaknesses | Missing | Week 4
☐ | 66 | Support App | Multi-channel ticketing (WhatsApp, Email, In-app, Phone) | HIGH | Omnichannel support — industry standard | Partial | Week 2
☐ | 67 | Support App | AI-powered auto-resolution for common issues | HIGH | Reduces support cost 60% — Zepto uses Freshdesk AI | Partial (Groq AI) | Week 2
☐ | 68 | Support App | SLA-based ticket priority & escalation workflow | HIGH | Response time SLA management | Missing | Week 2
☐ | 69 | Support App | Canned responses & knowledge base for agents | HIGH | Agent efficiency — reduces handle time 40% | Missing | Week 2
☐ | 70 | Support App | Automated order status update via WhatsApp | HIGH | Proactive communication reduces incoming calls 30% | Missing | Week 2
☐ | 71 | Support App | Refund workflow with auto-approval for <Rs200 orders | HIGH | Operational efficiency & customer delight | Missing | Week 2
☐ | 72 | Support App | Agent performance dashboard (AHT, CSAT, tickets/hour) | HIGH | Quality management for support team | Missing | Week 3
☐ | 73 | Support App | Customer sentiment analysis on tickets (AI) | MEDIUM | CSAT prediction — prevents churn | Missing | Week 4
☐ | 74 | Support App | Voice call integration (IVR + live agent) | MEDIUM | India: 40% customers prefer phone support | Missing | Week 5
☐ | 75 | Monitoring App | Distributed tracing (Jaeger / Zipkin integration) | HIGH | Root cause analysis across microservices | Missing | Week 2
☐ | 76 | Monitoring App | Real-time anomaly detection with auto-alerting | HIGH | Proactive issue detection — PagerDuty model | Missing | Week 2
☐ | 77 | Monitoring App | Business metrics dashboard (GMV, order/hr, success rate) | HIGH | Business + tech metrics in single pane | Partial (Grafana) | Week 2
☐ | 78 | Monitoring App | Cost per order tracking with profitability alerts | HIGH | Unit economics monitoring — critical for q-commerce | Missing | Week 3
☐ | 79 | Monitoring App | SLA compliance tracking per delivery zone | HIGH | Operational KPI monitoring | Missing | Week 3
☐ | 80 | Monitoring App | Rider utilization & idle time monitoring | HIGH | Fleet efficiency KPI | Missing | Week 3
☐ | 81 | Monitoring App | API latency percentile tracking (p50/p95/p99) | HIGH | Performance SLA monitoring | Partial | Week 2
☐ | 82 | Monitoring App | Error budget tracking (SLO/SLI/SLA framework) | MEDIUM | Site reliability engineering best practice | Missing | Week 4
☐ | 83 | Monitoring App | Dark store replenishment trigger monitoring | MEDIUM | Inventory health monitoring | Missing | Week 4
☐ | 84 | Monitoring App | Automated runbook execution on alert trigger | MEDIUM | Self-healing infrastructure — reduces MTTR 60% | Missing | Week 5

## UI-UX Enhancements
UI-UX ENHANCEMENTS — SUNOTAL ENHANCEMENTS (44 items)
Mark Done? column with ✓ when completed ¦ Priority: CRITICAL > HIGH > MEDIUM > LOW
Done? | # | Service / Module | Enhancement / Recommendation | Priority | Business Rationale | Current Status | Timeline | Notes / Remarks
☐ | 1 | User App | Sticky 10-min delivery countdown banner on homepage | HIGH | Creates urgency — Blinkit signature UI element | Missing | Week 1
☐ | 2 | User App | Bottom navigation bar with cart badge (mobile-first) | HIGH | 80% Indian users on mobile — bottom nav is standard | Missing | Week 1
☐ | 3 | User App | Infinite scroll with skeleton loading placeholders | HIGH | Perceived performance — reduces bounce rate | Missing | Week 1
☐ | 4 | User App | Swipeable product carousel with quick add-to-cart | HIGH | Reduces tap count — increases conversions | Missing | Week 1
☐ | 5 | User App | Progressive Web App (PWA) with offline fallback page | HIGH | Install-to-homescreen, works offline in low-signal areas | Missing | Week 2
☐ | 6 | User App | Animated delivery status progress timeline | HIGH | Emotional engagement — Swiggy-style status timeline | Partial | Week 1
☐ | 7 | User App | Geo-fenced location picker with saved addresses dropdown | HIGH | Reduces address entry friction | Partial | Week 1
☐ | 8 | User App | Quantity selector with +/- buttons (not dropdown) | HIGH | Quick-add UX pattern — cart edit simplicity | Missing | Week 1
☐ | 9 | User App | Smart search with autocomplete, trending & recent searches | HIGH | Reduces time-to-purchase significantly | Partial | Week 1
☐ | 10 | User App | Sticky cart summary bar during checkout | HIGH | Reduces cognitive load in checkout | Missing | Week 1
☐ | 11 | User App | One-page checkout (address + payment on single screen) | HIGH | Critical conversion optimization — Zepto pattern | Missing | Week 2
☐ | 12 | User App | Contextual upsell at checkout (frequently bought together) | HIGH | Increases AOV by 15-20% | Missing | Week 2
☐ | 13 | User App | Micro-animations on add-to-cart and wishlist actions | MEDIUM | Delight moments — increases engagement | Missing | Week 2
☐ | 14 | User App | Personalized 'Good Morning' home banner with quick adds | MEDIUM | Emotional connection — morning staples push | Missing | Week 2
☐ | 15 | User App | Empty state illustrations (empty cart, no results, error) | MEDIUM | Better UX for edge cases | Missing | Week 2
☐ | 16 | User App | In-line coupon code application in cart | MEDIUM | Reduces friction in checkout flow | Missing | Week 2
☐ | 17 | User App | Dark Mode UI toggle | MEDIUM | 65% users prefer dark mode — standard feature | Missing | Week 2
☐ | 18 | User App | Product image zoom & 360-degree view | MEDIUM | Trust builder for fresh produce | Missing | Week 3
☐ | 19 | User App | Accessibility (WCAG 2.1 AA) compliance | MEDIUM | Legal requirement + inclusivity | Missing | Week 4
☐ | 20 | Delivery App | Real-time earnings counter (animated Rs ticker during shift) | HIGH | Motivational — increases delivery acceptance rate | Missing | Week 2
☐ | 21 | Delivery App | Dark/Night mode optimized for riding conditions | HIGH | Rider safety — important for night deliveries | Missing | Week 1
☐ | 22 | Delivery App | Large-tap-target UI optimized for gloves / riding | HIGH | Rider ergonomics — Swiggy Sathi app pattern | Missing | Week 2
☐ | 23 | Delivery App | Turn-by-turn audio navigation (hands-free) | HIGH | Safety during riding — core feature | Missing | Week 2
☐ | 24 | Delivery App | Tap-to-call customer with masked number | HIGH | Privacy + convenience for rider | Missing | Week 1
☐ | 25 | Delivery App | OTP in large font with auto-copy from SMS | HIGH | Reduces time fumbling with OTP | Partial (no auto-copy) | Week 1
☐ | 26 | Delivery App | Vibration + alert sound for new order notification | HIGH | Ensures rider does not miss orders | Missing | Week 1
☐ | 27 | Delivery App | Order pack image preview (what to pick at dark store) | MEDIUM | Reduces wrong-item errors | Missing | Week 3
☐ | 28 | Vendor App | Mobile-first dashboard with thumb-friendly layout | HIGH | Most Indian farmers use mobile — not desktop | Missing | Week 2
☐ | 29 | Vendor App | One-tap stock update (in-stock / out-of-stock toggle) | HIGH | Quick inventory management on mobile | Missing | Week 1
☐ | 30 | Vendor App | Payment receipt download as PDF | HIGH | GST compliance for vendor bookkeeping | Missing | Week 2
☐ | 31 | Vendor App | Regional language support (Telugu, Hindi, Kannada) | HIGH | India inclusion — 70% vendors non-English | Missing | Week 3-4
☐ | 32 | Vendor App | Product listing quality score indicator | MEDIUM | Guides vendor to improve listings | Missing | Week 3
☐ | 33 | Admin App | Export to Excel/CSV from all data tables | HIGH | Operations team requirement | Missing | Week 2
☐ | 34 | Admin App | Interactive demand heatmap overlay on city map | HIGH | Visual operations intelligence | Missing | Week 3
☐ | 35 | Admin App | Collapsible sidebar with keyboard shortcuts | MEDIUM | Power user efficiency | Missing | Week 2
☐ | 36 | Admin App | Data table with inline editing (no separate form page) | MEDIUM | Operational speed for admin tasks | Missing | Week 3
☐ | 37 | Admin App | Responsive admin dashboard for mobile field managers | MEDIUM | Field operations use-case | Missing | Week 3
☐ | 38 | Admin App | Drag-and-drop dark store zone mapping on map | MEDIUM | Visual zone management | Missing | Week 4
☐ | 39 | Support App | Ticket timeline with all communications in one thread | HIGH | Context retention for multi-touch tickets | Missing | Week 2
☐ | 40 | Support App | Quick filter chips (by status, category, priority) | MEDIUM | Agent workflow efficiency | Missing | Week 2
☐ | 41 | Support App | Chat bubble with typing indicator | MEDIUM | Agent engagement UX | Missing | Week 3
☐ | 42 | Monitoring App | Real-time Grafana embed in monitoring app | HIGH | Integrated observability view | Partial (separate Grafana) | Week 2
☐ | 43 | Monitoring App | One-click incident creation from alert | HIGH | Reduces MTTD to MTTR gap | Missing | Week 3
☐ | 44 | Monitoring App | Service dependency graph visualization | MEDIUM | Impact analysis during incidents | Missing | Week 4

## DB Query CRUD Optimization
DB QUERY CRUD OPTIMIZATION — SUNOTAL ENHANCEMENTS (34 items)
Mark Done? column with ✓ when completed ¦ Priority: CRITICAL > HIGH > MEDIUM > LOW
Done? | # | Service / Module | Enhancement / Recommendation | Priority | Business Rationale | Current Status | Timeline | Notes / Remarks
☐ | 1 | User App Backend | Cursor-based (keyset) pagination for /api/products — avoid OFFSET | HIGH | OFFSET is O(n) — 50x slower on large product tables | Not Done | Week 1
☐ | 2 | User App Backend | GIN index on products(name) for full-text search with pg_trgm | HIGH | LIKE %search% does full table scan — 50x slower without GIN | Partial (gateway only) | Week 1
☐ | 3 | User App Backend | Cache /api/categories & /api/products in Redis (TTL 60s) | HIGH | Category data changes rarely — cache hits save 80% DB calls | Not Done | Week 1
☐ | 4 | User App Backend | Composite index on products(category, active, price) | HIGH | Multi-column filter without composite index = index merge overhead | Not Done | Week 1
☐ | 5 | User App Backend | Replace SELECT * with named column lists in all queries | MEDIUM | SELECT * over-fetches — adds network overhead | Not Done | Week 1
☐ | 6 | User App Backend | Batch wishlist checks using ANY($1) instead of N+1 queries | HIGH | N+1 query anti-pattern in wishlist toggle — fix immediately | Issue Present | Week 1
☐ | 7 | User App Backend | PgBouncer connection pooling between services and RDS | HIGH | Each service has own pool — wastes RDS connection slots | Not Done | Week 2
☐ | 8 | User App Backend | Database read replica for all GET endpoints | HIGH | Reduces primary DB load — critical for scale | Not Done | Week 3
☐ | 9 | User App Backend | RETURNING clause to all INSERT/UPDATE to avoid second SELECT | MEDIUM | Eliminates extra round-trip to DB | Partial | Week 1
☐ | 10 | Admin Backend | Single CTE query instead of 11 parallel queries in /api/admin/stats | HIGH | 11 parallel pool.query() calls waste connection pool | Issue Present | Week 1
☐ | 11 | Admin Backend | Materialized view for GMV/revenue stats with scheduled refresh | HIGH | Live aggregation on large orders table is expensive | Not Done | Week 2
☐ | 12 | Admin Backend | Partial indexes: orders WHERE status='placed' and 'out_for_delivery' | HIGH | Active order queries most frequent — partial idx speeds these up | Not Done | Week 1
☐ | 13 | Admin Backend | Row-level security (RLS) for multi-tenant data isolation | HIGH | Security & data isolation requirement | Not Done | Week 3
☐ | 14 | Admin Backend | pg_stat_statements extension for query performance monitoring | HIGH | Identifies slow queries automatically | Not Done | Week 1
☐ | 15 | Admin Backend | Batch inventory updates using UNNEST for bulk deductions | HIGH | Loop-based inventory deduction in delivery service is slow | Issue Present | Week 2
☐ | 16 | Admin Backend | BRIN index on orders(created_at) for time-range analytics | MEDIUM | BRIN efficient for append-only time-series data | Not Done | Week 2
☐ | 17 | Admin Backend | JSONB for dynamic product attributes (not many nullable columns) | MEDIUM | Flexible schema with indexed JSONB > EAV pattern | Not Done | Week 3
☐ | 18 | Admin Backend | Soft-delete pattern (deleted_at TIMESTAMP) for vendors/products | MEDIUM | Hard delete loses audit trail — data recovery impossible | Not Done | Week 2
☐ | 19 | Admin Backend | CHECK constraints on price, stock, rating columns | MEDIUM | DB-level data integrity enforcement | Not Done | Week 2
☐ | 20 | Delivery Backend | PostGIS extension for geospatial queries (nearest rider, zone) | HIGH | Haversine in app code slower than PostGIS spatial index | Not Done | Week 2
☐ | 21 | Delivery Backend | SKIP LOCKED for order assignment queue (prevent race conditions) | HIGH | Multiple riders can accept same order — needs atomic dequeue | Not Done | Week 2
☐ | 22 | Delivery Backend | Move rider GPS to Redis sorted set (not PostgreSQL) | HIGH | DB write per GPS update expensive — Redis O(log n) is optimal | Not Done | Week 2
☐ | 23 | Delivery Backend | Covering index on delivery_orders(status, rider_id, updated_at) | HIGH | Active delivery queries need this covering index | Not Done | Week 1
☐ | 24 | Delivery Backend | Partition delivery_orders table by month for archival | MEDIUM | Large delivery_orders table will slow over time | Not Done | Week 4
☐ | 25 | Vendor Backend | Cache vendor catalog data per vendor_id in Redis | MEDIUM | Vendor product listings fetched on every page load | Not Done | Week 2
☐ | 26 | Vendor Backend | Unique partial index on quotations WHERE status='PENDING' | MEDIUM | Prevent duplicate pending quotations | Not Done | Week 2
☐ | 27 | Support Backend | FTS index on support_tickets(subject, description) | MEDIUM | LIKE search on text inefficient for large ticket volumes | Not Done | Week 2
☐ | 28 | Support Backend | resolved_at timestamp column for SLA tracking queries | HIGH | Cannot compute resolution time without resolved_at column | Missing Column | Week 1
☐ | 29 | Support Backend | Ticket archival — move resolved tickets >90 days to archive table | MEDIUM | Keep active tickets table small for query performance | Not Done | Week 3
☐ | 30 | All Services | Redis-based idempotency keys for all POST endpoints | HIGH | Prevents duplicate order creation on network retry | Not Done | Week 2
☐ | 31 | All Services | DB health check with retry backoff on pool.connect() | HIGH | Services crash on DB restart instead of graceful reconnect | Not Done | Week 1
☐ | 32 | All Services | Centralize schema migrations to Flyway / Prisma Migrate | HIGH | Service startup blocking on migrations is anti-pattern | Not Done | Week 2-3
☐ | 33 | All Services | Query timeout parameter to all pool.query() calls (30s) | HIGH | Runaway queries can block entire connection pool | Not Done | Week 1
☐ | 34 | All Services | Connection pool monitoring with pg_pool_status metrics | MEDIUM | Detect pool exhaustion before it causes outage | Not Done | Week 2

## Dockerfile Optimization
DOCKERFILE OPTIMIZATION — SUNOTAL ENHANCEMENTS (18 items)
Mark Done? column with ✓ when completed ¦ Priority: CRITICAL > HIGH > MEDIUM > LOW
Done? | # | Service / Module | Enhancement / Recommendation | Priority | Business Rationale | Current Status | Timeline | Notes / Remarks
☐ | 1 | All Services | Multi-stage Docker builds (build stage vs runtime stage) | HIGH | Single stage includes devDependencies — image 2x larger than needed | Not Done | Week 1
☐ | 2 | All Services | Pin exact Node.js version: node:20.18.0-alpine3.20 | HIGH | Floating tag causes non-reproducible builds | Not Done | Week 1
☐ | 3 | All Services | Complete .dockerignore: node_modules, .git, dist, *.log | HIGH | Missing .dockerignore bloats Docker build context | Partial | Week 1
☐ | 4 | All Services | Run as non-root user (addgroup/adduser appuser) | HIGH | Security best practice — root in container = security risk | Not Done | Week 1
☐ | 5 | All Services | HEALTHCHECK instruction in Dockerfile (not just compose) | HIGH | Kubernetes/ECS needs Dockerfile HEALTHCHECK for liveness probe | Not Done | Week 1
☐ | 6 | All Services | Cache npm install: COPY package*.json BEFORE COPY . . | HIGH | Wrong COPY order breaks layer caching — slower CI builds | Not Done | Week 1
☐ | 7 | All Services | pnpm ci --frozen-lockfile for reproducible installs | HIGH | pnpm install without --frozen-lockfile can mutate lockfile | Not Done | Week 1
☐ | 8 | All Services | Remove devDependencies in production: pnpm prune --prod | HIGH | Reduces final image size by 40-60% | Not Done | Week 1
☐ | 9 | All Services | Add NODE_ENV=production ENV in Dockerfile | HIGH | Express + packages have faster code paths in production mode | Not Done | Week 1
☐ | 10 | All Services | COPY --chown=node:node to set correct file permissions | MEDIUM | Ensures correct permissions without separate chmod step | Not Done | Week 1
☐ | 11 | All Services | distroless/node:20 base for production stage | MEDIUM | Reduces image size 30%, eliminates shell attack vector | Not Done | Week 2
☐ | 12 | All Services | BuildKit cache mounts for pnpm store | MEDIUM | Speeds up CI/CD pipeline by 50% | Not Done | Week 2
☐ | 13 | All Services | Docker image vulnerability scanning (Trivy/Snyk) in CI | HIGH | .trivyignore exists but no CI pipeline scanning configured | Partial | Week 2
☐ | 14 | All Services | NODE_OPTIONS=--max-old-space-size=512 to prevent OOM | MEDIUM | Prevents Node.js OOM crashes in memory-constrained containers | Not Done | Week 2
☐ | 15 | Frontend Services | Nginx nginx.conf with gzip compression enabled | HIGH | Gzip reduces static asset size by 70% | Missing | Week 1
☐ | 16 | Frontend Services | Cache-Control headers for static assets (1 year for hashed) | HIGH | Browser caching — reduces CDN origin hits by 90% | Missing | Week 1
☐ | 17 | Frontend Services | Vite build with --mode production, sourcemaps disabled | MEDIUM | Sourcemaps in production expose internal source code | Not Done | Week 1
☐ | 18 | All Services | LABEL metadata (version, maintainer, build date) on images | LOW | Image management and auditability in ECR | Not Done | Week 2

## DockerCompose Optimization
DOCKERCOMPOSE OPTIMIZATION — SUNOTAL ENHANCEMENTS (17 items)
Mark Done? column with ✓ when completed ¦ Priority: CRITICAL > HIGH > MEDIUM > LOW
Done? | # | Service / Module | Enhancement / Recommendation | Priority | Business Rationale | Current Status | Timeline | Notes / Remarks
☐ | 1 | docker-compose.yml | Resource limits (mem_limit, cpus) for all containers | HIGH | Without limits, one service can OOM the entire host | Not Done | Week 1
☐ | 2 | docker-compose.yml | Logging driver with max-size and max-file (prevent disk fill) | HIGH | No log rotation = disk fill = service crash | Not Done | Week 1
☐ | 3 | docker-compose.yml | Redis password authentication (requirepass) in Redis command | HIGH | Redis running without auth = major security risk | Not Done | Week 1
☐ | 4 | docker-compose.yml | PostgreSQL tuning: shared_buffers, work_mem, max_connections | HIGH | Default Postgres config not tuned for application workloads | Not Done | Week 1
☐ | 5 | docker-compose.yml | MongoDB auth env vars (MONGO_INITDB_ROOT_USERNAME/PASSWORD) | HIGH | MongoDB running without authentication in compose | Not Done | Week 1
☐ | 6 | docker-compose.yml | Reduce ports exposure — only expose nginx on 80/443 | HIGH | All backends exposed on host ports = security risk | Not Done | Week 1
☐ | 7 | docker-compose.yml | init: true for all Node.js services (proper SIGTERM handling) | MEDIUM | Without init, Node.js does not receive SIGTERM cleanly | Not Done | Week 1
☐ | 8 | docker-compose.yml | depends_on with service_healthy for ALL inter-service deps | HIGH | Services start before dependencies are healthy | Partial | Week 1
☐ | 9 | docker-compose.yml | Named secrets instead of environment variables for credentials | HIGH | Env var credentials visible in docker inspect output | Not Done | Week 2
☐ | 10 | docker-compose.yml | Isolated networks: frontend_net, backend_net, db_net | HIGH | All services on default network = lateral movement risk | Not Done | Week 2
☐ | 11 | docker-compose.yml | docker-compose.override.yml for dev-specific settings | MEDIUM | Dev/prod separation best practice | Not Done | Week 2
☐ | 12 | docker-compose.yml | restart: on-failure:3 instead of unless-stopped | MEDIUM | unless-stopped masks crash loops — on-failure:3 is safer | Not Done | Week 2
☐ | 13 | docker-compose.yml | Prometheus & Grafana in compose with pre-built dashboards | HIGH | Monitoring stack not part of default compose up | Partial | Week 2
☐ | 14 | docker-compose.yml | Explicit image version pinning (no :latest or :alpine tags) | MEDIUM | Floating tags cause unexpected updates in production | Not Done | Week 2
☐ | 15 | docker-compose.yml | docker-compose.test.yml for integration test runs | MEDIUM | Isolated test environment with test DB | Not Done | Week 3
☐ | 16 | docker-compose.yml | tmpfs mount for Redis when used as pure cache (disable AOF) | LOW | If Redis is cache-only, disable persistence for performance | Not Done | Week 3
☐ | 17 | docker-compose.yml | MongoDB healthcheck with proper mongosh --eval command | MEDIUM | Current healthcheck may fail on auth-enabled clusters | Partial | Week 1

## Terraform Code Optimization
TERRAFORM CODE OPTIMIZATION — SUNOTAL ENHANCEMENTS (20 items)
Mark Done? column with ✓ when completed ¦ Priority: CRITICAL > HIGH > MEDIUM > LOW
Done? | # | Service / Module | Enhancement / Recommendation | Priority | Business Rationale | Current Status | Timeline | Notes / Remarks
☐ | 1 | terraform/modules/rds | RDS Multi-AZ failover configuration for production | HIGH | Single-AZ RDS = single point of failure — data risk | Not Done | Week 2
☐ | 2 | terraform/modules/rds | RDS automated backups — 7-day retention + point-in-time restore | HIGH | No data recovery capability configured | Not Done | Week 1
☐ | 3 | terraform/modules/rds | RDS deletion_protection = true for production | HIGH | Prevent accidental database deletion | Not Done | Week 1
☐ | 4 | terraform/modules/rds | RDS parameter group with custom Postgres tuning | MEDIUM | Default parameter group not optimized for workload | Not Done | Week 2
☐ | 5 | terraform/modules/elasticache | ElastiCache Redis cluster mode (not single node) | HIGH | Single Redis node = cache unavailable during maintenance | Not Done | Week 2
☐ | 6 | terraform/modules/ecs | ECS Auto-Scaling based on CPU/Memory/RequestCount | HIGH | Static task count cannot handle traffic spikes | Not Done | Week 2
☐ | 7 | terraform/modules/acm_alb | WAF rule group attached to ALB | HIGH | Missing WAF = SQL injection, OWASP Top 10 exposure | Not Done | Week 2
☐ | 8 | terraform/modules | AWS GuardDuty for threat detection | HIGH | Automated threat intelligence for AWS workload | Not Done | Week 2
☐ | 9 | terraform/modules | AWS Secrets Manager for all application secrets | HIGH | Credentials in ECS task env vars = security risk | Not Done | Week 2
☐ | 10 | terraform/modules/s3_cloudfront | S3 versioning and server-side encryption (SSE-KMS) | HIGH | Data protection for product images and documents | Not Done | Week 1
☐ | 11 | terraform/modules/cloudwatch | CloudWatch Container Insights for ECS cluster | HIGH | Container-level metrics for scaling decisions | Not Done | Week 1
☐ | 12 | terraform/modules/sqs_sns | SQS dead-letter queues (DLQ) for all SQS queues | HIGH | Failed messages lost without DLQ — SQS module exists | Not Done | Week 2
☐ | 13 | terraform/modules | AWS Backup plan for RDS and EFS resources | HIGH | Centralized backup management and compliance | Not Done | Week 2
☐ | 14 | terraform/modules/vpc | VPC Flow Logs for network traffic auditing | MEDIUM | Security compliance & incident investigation | Not Done | Week 2
☐ | 15 | terraform/modules/ecr | ECR image lifecycle policy (auto-clean untagged images) | MEDIUM | ECR storage costs accumulate without cleanup policy | Not Done | Week 1
☐ | 16 | terraform/modules/s3_cloudfront | CloudFront OAC replacing legacy OAI | MEDIUM | OAI deprecated by AWS — OAC is current standard | Not Done | Week 2
☐ | 17 | terraform/ | Terraform workspaces for dev/staging/prod separation | HIGH | Single environment config — no isolation between envs | Not Done | Week 2
☐ | 18 | terraform/modules/acm_alb | ALB access logs to S3 for compliance and debugging | MEDIUM | Request-level audit trail for security investigations | Not Done | Week 2
☐ | 19 | terraform/modules/vpc | NAT instance for dev (not NAT Gateway) — saves $27/month | MEDIUM | NAT Gateway $32/month vs NAT instance $5/month for dev | Not Done | Week 2
☐ | 20 | terraform/ | Tagging strategy enforcement with required tag validation | LOW | Consistent tagging for cost allocation and governance | Partial | Week 3

## Workflow Optimization
WORKFLOW OPTIMIZATION — SUNOTAL ENHANCEMENTS (25 items)
Mark Done? column with ✓ when completed ¦ Priority: CRITICAL > HIGH > MEDIUM > LOW
Done? | # | Service / Module | Enhancement / Recommendation | Priority | Business Rationale | Current Status | Timeline | Notes / Remarks
☐ | 1 | CI/CD | GitHub Actions CI: lint + test + build + docker push | HIGH | .github folder exists but no workflow YAML present | Missing | Week 1
☐ | 2 | CI/CD | Automated integration tests with Docker Compose test env | HIGH | No integration tests — releases are untested | Missing | Week 2
☐ | 3 | CI/CD | Blue-green deployment for zero-downtime releases on ECS | HIGH | Current deployment causes service downtime | Missing | Week 3
☐ | 4 | CI/CD | Trivy security scan in CI before image push to ECR | HIGH | .trivyignore exists but no CI scanning pipeline | Missing | Week 2
☐ | 5 | CI/CD | Semantic versioning with auto-changelog generation | MEDIUM | No version tracking across microservices | Missing | Week 3
☐ | 6 | CI/CD | Renovate Bot / Dependabot for dependency updates | MEDIUM | Stale dependencies accumulate security vulnerabilities | Missing | Week 2
☐ | 7 | CI/CD | Canary deployments with traffic split (10% > 50% > 100%) | HIGH | Risk mitigation for production releases | Missing | Week 4
☐ | 8 | CI/CD | PR-based preview environments using ECS on-demand tasks | MEDIUM | Faster developer feedback loop | Missing | Week 4
☐ | 9 | Development | Modular route/controller/service structure (not monolithic index.ts) | HIGH | 2000+ line index.ts is unmaintainable — critical tech debt | Not Done | Week 2-3
☐ | 10 | Development | Shared TypeScript types package across all services (monorepo) | HIGH | Type duplication across services — divergence risk | Not Done | Week 2
☐ | 11 | Development | API contract testing with OpenAPI/Swagger spec generation | MEDIUM | No API documentation or contract validation | Missing | Week 3
☐ | 12 | Development | Event-driven architecture with SQS for order state transitions | HIGH | Direct DB polling/SSE not scalable — SQS provisioned but unused | Not Done | Week 3-4
☐ | 13 | Development | Circuit breaker pattern for inter-service HTTP calls | HIGH | Service cascade failures with no circuit breaker | Missing | Week 3
☐ | 14 | Development | Structured JSON logging with log levels across all services | HIGH | console.log in production — not searchable or filterable | Not Done | Week 1
☐ | 15 | Development | Graceful shutdown handling (SIGTERM) in all services | HIGH | Services drop in-flight requests on restart | Missing | Week 1
☐ | 16 | Development | Rate limiting middleware on gateway (Redis sliding window) | HIGH | No rate limiting = DoS vulnerability | Missing | Week 1
☐ | 17 | Development | Request validation middleware using Zod/Joi schemas | HIGH | Manual validation scattered across routes — error prone | Not Done | Week 2
☐ | 18 | Development | Correlation ID propagation across all service-to-service calls | HIGH | Partial in gateway only — not propagated to other services | Partial | Week 2
☐ | 19 | Delivery Operations | Auto order-to-rider assignment algorithm (geospatial) | HIGH | Manual assignment is the bottleneck for 10-min SLA | Missing | Week 3
☐ | 20 | Delivery Operations | Rider shift scheduling system with capacity planning | MEDIUM | Workforce management for peak hours | Missing | Week 4
☐ | 21 | Delivery Operations | Dynamic delivery zone management based on rider density | HIGH | Static zones do not adapt to real supply/demand | Missing | Week 4
☐ | 22 | Delivery Operations | Auto-escalation when order exceeds SLA time | HIGH | No SLA breach automation — manual ops intervention needed | Missing | Week 3
☐ | 23 | Procurement | Auto procurement trigger when inventory < reorder point | HIGH | Manual procurement tracking is error-prone | Missing | Week 3
☐ | 24 | Procurement | Vendor onboarding checklist with document verification | HIGH | Manual vendor verification — compliance risk | Missing | Week 3
☐ | 25 | Procurement | Quality sampling workflow with photo evidence at inbound | MEDIUM | Quality gate at dark store inbound | Missing | Week 4

## System Design Optimization
SYSTEM DESIGN OPTIMIZATION — SUNOTAL ENHANCEMENTS (21 items)
Mark Done? column with ✓ when completed ¦ Priority: CRITICAL > HIGH > MEDIUM > LOW
Done? | # | Service / Module | Enhancement / Recommendation | Priority | Business Rationale | Current Status | Timeline | Notes / Remarks
☐ | 1 | Architecture | WebSocket + Redis pub/sub for rider GPS (not SSE+DB polling) | HIGH | SSE with DB polling O(n) per update — WebSocket+Redis is O(1) | Not Done | Week 2
☐ | 2 | Architecture | API Gateway pattern with proper routing and load balancing | HIGH | Gateway does everything — violates single responsibility principle | Not Done | Week 3
☐ | 3 | Architecture | SQS for order processing to decouple services | HIGH | Direct service calls = tight coupling — SQS provisioned but unused | Not Done | Week 3
☐ | 4 | Architecture | Redis caching layer for product catalog (cache-aside pattern) | HIGH | Product catalog queried on every page load — zero caching | Not Done | Week 1
☐ | 5 | Architecture | Outbox pattern for reliable event publishing on order changes | HIGH | Lost events cause inconsistent state across services | Missing | Week 4
☐ | 6 | Architecture | API versioning (/api/v1/ prefix) for backward compatibility | HIGH | No versioning — breaking changes affect all clients simultaneously | Missing | Week 2
☐ | 7 | Architecture | Distributed session management with Redis | HIGH | JWT stateless but rider/vendor sessions need Redis-backed state | Missing | Week 2
☐ | 8 | Architecture | Idempotent order placement with distributed locks (Redis SETNX) | HIGH | Duplicate orders on network retry — critical business bug | Missing | Week 2
☐ | 9 | Architecture | CQRS for order service (read replica for all queries) | MEDIUM | High-read order status queries should not hit primary DB | Not Done | Week 5
☐ | 10 | Architecture | Multi-region failover for business continuity | MEDIUM | Single-region = region outage = complete platform downtime | Not Done | Week 8
☐ | 11 | Database | Read replicas for all analytical/reporting queries | HIGH | Reporting queries on primary DB impact write performance | Not Done | Week 2
☐ | 12 | Database | Data archival: orders > 1 year to S3 + Athena | MEDIUM | Active table size grows indefinitely — query performance degrades | Not Done | Week 6
☐ | 13 | Database | Connection pool monitoring and auto-scaling | HIGH | Pool exhaustion silently queues requests — no visibility | Not Done | Week 2
☐ | 14 | Database | Change Data Capture (CDC) with Debezium for event streaming | MEDIUM | Real-time event propagation from DB changes to downstream services | Not Done | Week 6
☐ | 15 | Security | OAuth 2.0 / OIDC with refresh token rotation | HIGH | Current JWT implementation basic — no refresh token mechanism | Not Done | Week 2
☐ | 16 | Security | RBAC at middleware level (not scattered in route handlers) | HIGH | Role checks scattered in route handlers — not centralized | Not Done | Week 2
☐ | 17 | Security | PII encryption at rest (phone, Aadhaar, bank account) | HIGH | Personal data in plaintext — DPDPA compliance violation | Not Done | Week 2
☐ | 18 | Security | HMAC request signing for service-to-service calls | HIGH | No authentication between internal microservices | Missing | Week 3
☐ | 19 | Security | CORS policy restriction (specific origins not origin: true) | HIGH | CORS wildcard allows any domain to make authenticated requests | Not Done | Week 1
☐ | 20 | Security | Request size limiting on express.json() | MEDIUM | Large payload DoS attacks possible — no limit set | Missing | Week 1
☐ | 21 | Security | API key management for B2B vendor integrations | MEDIUM | No API key issuance/rotation mechanism | Missing | Week 4

## Business Logic Corrections
BUSINESS LOGIC CORRECTIONS — SUNOTAL ENHANCEMENTS (34 items)
Mark Done? column with ✓ when completed ¦ Priority: CRITICAL > HIGH > MEDIUM > LOW
Done? | # | Service / Module | Enhancement / Recommendation | Priority | Business Rationale | Current Status | Timeline | Notes / Remarks
☐ | 1 | Delivery Service | CRITICAL BUG: OTP '123456'/'1234' hardcoded as valid OTPs | CRITICAL | Backdoor OTP allows anyone to mark order delivered — FRAUD RISK! | Bug Present | Immediate
☐ | 2 | Delivery Service | CRITICAL BUG: Rider auto-APPROVED on registration (skip KYC) | CRITICAL | status=APPROVED hardcoded — anyone can become a delivery rider | Bug Present | Immediate
☐ | 3 | Vendor Service | CRITICAL BUG: Default vendor password hardcoded as 'password123' | CRITICAL | Default weak password for ALL vendor accounts = security hole | Bug Present | Immediate
☐ | 4 | Vendor Service | CRITICAL: Bank account numbers not encrypted at rest | CRITICAL | DPDPA / RBI data localization compliance violation | Bug Present | Immediate
☐ | 5 | Admin Service | CRITICAL: /api/admin/settings accessible WITHOUT JWT auth | CRITICAL | Unauthenticated PUT can modify ALL platform settings | Bug Present | Immediate
☐ | 6 | All Services | CRITICAL: JWT secret defaults to 'sunotal-jwt-secret' | CRITICAL | Hardcoded weak JWT secret = authentication bypass possible | Bug Present | Immediate
☐ | 7 | All Services | CRITICAL: CORS set to origin:true for all services | CRITICAL | CSRF attacks possible from any domain — fix immediately | Bug Present | Immediate
☐ | 8 | User/Admin | Wallet deduction not atomic — race condition on concurrent orders | HIGH | Two concurrent orders can both succeed with insufficient balance | Bug Present | Week 1
☐ | 9 | User/Admin | Coupon used_count not incremented atomically — flash sale race | HIGH | Multiple users can exceed coupon usage_limit during flash sale | Bug Present | Week 1
☐ | 10 | User/Admin | Stock deduction at 'picked_up' not 'order_placed' — OVERSELLING | HIGH | Overselling possible between order placement and pickup | Bug Present | Week 1
☐ | 11 | User/Admin | Delivery fee: per_km_rate in DB but NOT used in checkout calc | HIGH | Delivery fee may be incorrect — using static hardcoded values | Bug Present | Week 1
☐ | 12 | User/Admin | Order total missing tax validation — GST not calculated correctly | HIGH | GST not applied correctly for all product categories | Bug Present | Week 1
☐ | 13 | User/Admin | Password strength validation missing before hashing | HIGH | Users can set single-character passwords | Missing | Week 1
☐ | 14 | User/Admin | Referral code column exists but never populated or validated | MEDIUM | Referral system incomplete — dead code in database schema | Bug Present | Week 2
☐ | 15 | Delivery Service | Payout credit hardcoded at Rs45 — should be dynamic (distance/value) | HIGH | Fixed payout ignores distance-based fair economics | Bug Present | Week 1
☐ | 16 | Delivery Service | Rider ID generated as timestamp — collision risk under concurrency | HIGH | r_${Date.now()} can collide under concurrent registrations | Bug Present | Week 1
☐ | 17 | Delivery Service | ETA uses fixed 25km/h speed — no traffic/time-of-day factor | MEDIUM | Inaccurate ETA damages customer trust and brand promise | Bug Present | Week 2
☐ | 18 | Delivery Service | GPS destination = current_lat + 0.015 offset — WRONG algorithm | HIGH | Placeholder math used as destination — not actual delivery address | Bug Present | Week 1
☐ | 19 | Delivery Service | Delivery slot hardcoded — not based on warehouse capacity | HIGH | Static slots do not reflect real warehouse capacity | Bug Present | Week 2
☐ | 20 | Admin Service | AWS cost calculation hardcoded (not from Cost Explorer API) | HIGH | Static cost figures are inaccurate and misleading in dashboard | Bug Present | Week 2
☐ | 21 | Admin Service | deliverySuccessRate hardcoded to 100 in admin stats | HIGH | Misleading metric — real success rate not being tracked | Bug Present | Week 1
☐ | 22 | Admin Service | Quotation price markup fixed at 10% — no configurable margin | MEDIUM | Margin should be configurable per category and vendor tier | Bug Present | Week 2
☐ | 23 | Admin Service | Invoice flag set without actual PDF generation | HIGH | GST compliance — invoices marked generated but no PDF exists | Bug Present | Week 2
☐ | 24 | Vendor Service | Vendor auto-approved via admin registration (bypasses KYC) | HIGH | Admin registration route bypasses onboarding workflow | Bug Present | Week 1
☐ | 25 | Vendor Service | Quotation ID uses Math.random() — not unique under concurrency | MEDIUM | QUOTE-XXXX collision possible in high-volume scenarios | Bug Present | Week 1
☐ | 26 | Vendor Service | GST invoice missing — TDS deduction not implemented | HIGH | Tax compliance — TDS @2% on vendor payments > Rs30,000 | Missing | Week 3
☐ | 27 | Support Service | AI chat has no rate limiting — Groq API abuse possible | HIGH | Groq API has per-minute limits — no user-level rate limiting | Bug Present | Week 1
☐ | 28 | Support Service | Ticket resolution does not notify user (no email/SMS/push) | HIGH | Customers never know their ticket was resolved | Missing | Week 2
☐ | 29 | Support Service | No SLA tracking — ticket created_at exists but no breach detection | HIGH | Support SLA promises unenforceable without tracking | Missing | Week 1
☐ | 30 | Support Service | Ticket ID not guaranteed unique under high load | MEDIUM | TKT-2026-${timestamp} can collide under concurrent creation | Bug Present | Week 1
☐ | 31 | All Services | Error messages expose internal stack traces to clients | HIGH | Information disclosure — err?.message leaked to client in 500s | Bug Present | Week 1
☐ | 32 | All Services | No XSS input sanitization on text fields | HIGH | Stored XSS possible via vendor product descriptions | Missing | Week 1
☐ | 33 | All Services | No request size limiting on express.json() | MEDIUM | Large payload DoS attacks possible | Missing | Week 1
☐ | 34 | All Services | Service-to-service calls use plain HTTP without authentication | HIGH | Internal API calls can be spoofed within network | Bug Present | Week 2

## Progress Tracker
SUNOTAL ENHANCEMENT PROGRESS TRACKER
Category | Total | Completed | In Progress | Not Started | % Complete
Application Features | 84 | 0 | 0 | 84 | 0%
UI-UX Enhancements | 44 | 0 | 0 | 44 | 0%
DB Query CRUD Optimization | 34 | 0 | 0 | 34 | 0%
Dockerfile Optimization | 18 | 0 | 0 | 18 | 0%
DockerCompose Optimization | 17 | 0 | 0 | 17 | 0%
Terraform Code Optimization | 20 | 0 | 0 | 20 | 0%
Workflow Optimization | 25 | 0 | 0 | 25 | 0%
System Design Optimization | 21 | 0 | 0 | 21 | 0%
Business Logic Corrections | 34 | 0 | 0 | 34 | 0%
TOTAL |  | 297